## Estimated Costs
Estimated Project Costs (Some Fields May Not be Applicable to Every Project)
| PROJECT TASKS | LABOR HOURS | LABOR COST ($) | MATERIAL COST ($) | TRAVEL COST ($) | OTHER COST ($) | TOTAL PER TASK
PROJECT DESIGN | Develop Functional Specifications | 20 | 1200 | 900 | 200 | 200 | 2500
| Develop System Architecture | 25 | 2000 | 700 | 200 | 100 | 3000
| Develop Preliminary Design Specification | 30 | 3000 | 800 | 150 | 50 | 4000
| Develop Detailed Design Specifications | 25 | 3000 | 1200 | 200 | 100 | 4500
| Develop Acceptance Test Plan | 20 | 1200 | 500 | 250 | 50 | 2000
| Subtotal | 120 | 10400 | 4100 | 1000 | 500 | 16000
PROJECT DEVELOPMENT | Develop Components | 20 | 2000 | 700 | 200 | 100 | 3000
| Procure Software | 40 | 15000 | 4500 | 1000 | 500 | 21000
| Procure Hardware | 30 | 3000 | 3500 | 100 | 500 | 7100
| Development Acceptance Test Package | 20 | 2000 | 700 | 200 | 100 | 3000
| Perform Unit/Integration Test | 24 | 2500 | 1000 | 400 | 100 | 4000
| Subtotal | 134 | 24500 | 10400 | 1900 | 1300 | 38100
PROJECT DELIVERY | Install System | 15 | 2000 | 1000 | 400 | 100 | 3500
| Train Customers | 25 | 1200 | 1500 | 250 | 50 | 3000
| Perform Acceptance Test | 7 | 500 | 300 | 150 | 50 | 1000
| Perform Post Project Review | 8 | 400 | 50 | 50 | 0 | 500
| Provide Warranty Support | 0 | 0 | 0 | 0 | 0 | 0
| Archive Materials | 0 | 0 | 0 | 0 | 0 | 0
| Subtotal | 55 | 4100 | 2850 | 850 | 200 | 8000
PROJECT MANAGEMENT | Customer Progress Meetings/Reports | 17 | 1500 | 300 | 100 | 100 | 2000
| Internal Status Meetings/Reports | 15 | 800 | 100 | 0 | 100 | 1000
| Third-Party Vendor Interface | 15 | 1700 | 500 | 200 | 100 | 2500
| Interface to Other Internal Departments | 30 | 1500 | 1000 | 400 | 100 | 3000
| Configuration Management | 0 | 0 | 0 | 0 | 0 | 0
| Quality Assurance | 0 | 0 | 0 | 0 | 0 | 0
| Overall Project Management | 20 | 1000 | 300 | 150 | 50 | 1500
| Subtotal | 97 | 6500 | 2200 | 850 | 450 | 10000
OTHER COST | Other cost | 6 | 700 | 500 | 200 | 100 | 1500
| Other cost | 4 | 500 | 400 | 200 | 100 | 1200
| Other cost | 0 | 0 | 0 | 0 | 0 | 0
| Subtotal | 10 | 1200 | 900 | 400 | 200 | 2700
Subtotals |  | 416 | 46700 | 20450 | 5000 | 2650 | 74800
Risk (Contingency) |  | 40 | 4000 | 2000 | 500 | 250 | 6750
Total (Scheduled) |  | 456 | 50700 | 22450 | 5500 | 2900 | 81550

## Actual Costs
Expenditures Over Time | Actual Project Costs (Some Fields May Not be Applicable to Every Project)
|  | ITEM | COST | DATE | REASON FOR EXPENDITURE
| PROJECT DESIGN | Develop Functional Specifications | 2300 | 2022-02-03 | For labour and material
|  | Develop System Architecture | 2800 | 2022-02-07 | Data collection
|  | Develop Preliminary Design Specification | 4200 | 2022-02-11 | To conduct cohort survey for better design
|  | Develop Detailed Design Specifications | 5000 | 2022-02-16 | Collaborative
|  | Develop Acceptance Test Plan | 1900 | 2022-02-21 | Interation, motion design and testing infrastructure design
|  | Subtotal | 16200
| PROJECT DEVELOPMENT | Develop Components | 2500 | 2022-02-25 | Application with an existing EHR tools
|  | Procure Software | 22000 | 2022-03-01 | Utilising software for app development
|  | Procure Hardware | 6000 | 2022-03-01 | In order to buy surver and in house wearables
|  | Development Acceptance Test Package | 2800 | 2022-03-05 | Collaboration between developers, testers, and business customers is emphasized.
|  | Perform Unit/Integration Test | 4200 | 2022-03-07 | Team for testing app and workflow.
|  | Subtotal | 37500
| PROJECT DELIVERY | Install System | 3200 | 2022-03-10 | App exposure on Apple's App Store and Google's Play Store
|  | Train Customers | 3500 | 2022-03-12 | Training end users how to use the application in different settings and taking their feedbacks for future developments
|  | Perform Acceptance Test | 800 | 2022-03-13 | Any bugs or errors have to be fixed, according to the development team.
|  | Perform Post Project Review | 500 | 2022-03-15 | Discussing issues that will be affecting the project
|  | Provide Warranty Support | 100 | 2022-03-16
|  | Archive Materials | 0
|  | Subtotal | 8100
| PROJECT MANAGEMENT | Customer Progress Meetings/Reports | 2500 | 2022-03-20 | Obtain input from the entire team involving end users.
|  | Internal Status Meetings/Reports | 500 | 2022-03-21 | Team for maintaing app
|  | Third-Party Vendor Interface | 1500 | 2022-03-25 | Verifying the suppliers and service providers
|  | Interface to Other Internal Departments | 3000 | 2022-03-27 | Development of User Interfaces
|  | Configuration Management | 500 | 2022-04-05 | Enables businesses to share data and functionality from their app applications with external third-party developers, vendors, and functional departments.
|  | Quality Assurance | 1500 | 2022-04-12 | Design inspection and static analysis are used to ensure software quality.
|  | Overall Project Management | 2000 | 2022-04-19 | ensuring that the project stays on track in terms of money, time, scope, and quality
|  | Subtotal | 11500
| OTHERS COST | Application launch and Licensing | 1000 |  | Creating installer for the application with license and delivering it to the markets like App Store, Google play
|  | Marketing Application | 1000 |  | Organizing a marketing campaign to raise awareness of the application.
|  | Maintainance Cost | 500 |  | Update, alter, and re-evaluate the program on a regular basis to solve errors and enhance performance.
|  | Subtotal | 2500
| PROJECT TOTAL |  | 75800

## Cumulative Project Costs
Projected vs. Actual Costs Diagram
MONTHLY COST
CUMULATIVE COST

## Data Worksheet
Project Data Worksheet
| WEEK | PROJECTED WEEKLY COST | ACTUAL WEEKLY COST | PROJECTED CUMULATIVE COST | ACTUAL CUMULATIVE COST
| 1 | 9000 | 2300 | 9000 | 2300
| 2 | 7000 | 7000 | 16000 | 9300
| 3 | 23000 | 5000 | 39000 | 14300
| 4 | 11000 | 4400 | 50000 | 18700
| 5 | 10500 | 30800 | 60500 | 49500
| 6 | 1500 | 10900 | 62000 | 60400
| 7 | 0 | 1400 | 62000 | 61800
| 8 | 3000 | 4500 | 65000 | 66300
| 9 | 5600 | 3000 | 70600 | 69300
| 10 | 1500 | 500 | 72100 | 69800
| 11 | 1500 | 1500 | 73600 | 71300
| 12 | 1200 | 2000 | 74800 | 73300