## Sheet1
Project Risk Analysis : B505 Team 1
ADR reporting mobile application
Group:B505 Team 1
Risk Number | Status | Risk Name | Description | Likelihood of Occurrence (1-5) | Impact (1-5) | Ease of Detectability (1-5) | Risk Priority Number | Date Opened | Risk Owner | Date Closed
1 | Closed | Scope creep | Improper definition of project scope or changes in scope of project due to change in stakeholder requirements | 3 | 4 | 2 | 24 | 2022-02-07 | Project manager | 2022-02-15
2 | Open | Technical glitches while integrating application with EHRs | All the informationin the EHR's might not be extracted | 3 | 4 | 3 | 36 | 2022-02-10 | Team members
3 | Closed | Budget constraints | Lack of sufficient budget for project continuationa and delay in receiving financial resources | 2 | 3 | 3 | 18 | 2022-02-20 | Project sponsor | 2022-03-15
4 | Closed | Data loss | Improper storage of data | 1 | 2 | 2 | 4 | 2022-02-20 | Team manager | 2022-03-30
5 | Open | Testing errors | failure of testing | 3 | 4 | 4 | 48 | 2022-02-20 | Team members
6 | Closed | Analysis of mobile application | Lack of Quality analysis | 2 | 3 | 3 | 18 | 2022-03-10 | Team members | 2022-03-15
7 | Closed | Communication errors | Failure of communication measures like emails and messaging applications and difficulty in communication due to team player's different timezones | 3 | 4 | 5 | 60 | 2022-03-12 | Project manager | 2022-03-16
8 | Closed | Non-adherence of physicians towards the app | Physicians and healthcare professionals missing the reporting due to external factors | 2 | 1 | 5 | 10 | 2022-03-13 | Project manager | 2022-03-24
9 | Open | Application construction and design | Lack of technical personnel resposible for design and construction of application | 2 | 3 | 4 | 24 | 2022-03-13 | Team members
10 | Closed | Compatibility issues with several software (iOS, Android) | leaving to the high cost of management | 4 | 4 | 4 | 64 | 2022-03-15 | Team members | 2022-03-17
11 | Closed | Change in legal requirements by regulatory authorities | Regulatory authorities and government agencies can change the standards required based on other factors | 2 | 1 | 4 | 8 | 2022-03-15 | Project sponsor | 2022-03-18
12 | Closed | Health data Misuse or data theft | The confidential health data regarding patients condition stored online can be misued or stolen due to security issues | 1 | 1 | 3 | 3 | 2022-03-17 | Project manager | 2022-03-19
14 | Closed | Low performance | Performance of the team players in the project has the potential to reduce due to lack of knowledge on subject | 2 | 3 | 3 | 18 | 2022-03-26 | Team members | 2022-03-28
15 | Open | Operational changes | Miscommunication with the team members by the manager | 3 | 4 | 4 | 48 | 2022-04-14 | Project manager
16 | Open | Lack of data strategy | Missing Structured planning | 2 | 3 | 3 | 18 | 2022-04-14 | Project manager
17 | Open | Market risk | Chance of change in market demand due to other available options like web applications | 3 | 4 | 3 | 36 | 2022-04-15 | Project manager
18 | Open | No control of access to external databases | Improper planning in acquiring the databases required | 1 | 3 | 4 | 12 | 2022-04-19 | Project sponsor
19 | Open | Lack of experience on handling personal data | Proper trainings have tobe provided to team members | 2 | 4 | 3 | 24 | 2022-04-20 | Project manager
20 | Open | Time Constraints | Lack of time due to unexpected errors during other phases of project | 4 | 4 | 3 | 48 | 2022-04-25 | Stake holders
0
1. Prioritize your risks according to their RPN
Compatibility issues with several software (iOS, Android)
Communication errors
Testing
Operational changes
Lack of experience on handling personal data, Technical glitches while integrating application with EHRs |  |  | Technical glitches while integrating application with EHRs
No control of access to external databases
Scope creep, Compatibility issues with several software (iOS, Android), Lack of experience on handling personal data
Budget constraints
Analysis of mobile application
Low performance
Lack of data strategy
No control of access to external databases
Change in legal requirements by regulatory authorities
Data loss
Health data Misuse or data theft
2. Provide a risk mitigation strategy for each risk
Compatibility issues with several software (iOS, Android) |  |  | A Specific testing team has to be assigned and the application has to be released as a pilot application before launching into the market
Communication errors |  |  | Team manager has to be preceise and up to date with the team members and have to keep updating the project status, He also should convey the team members what he expects from them
Testing |  |  | Multiple testing on the application has to be done by the testing team in order to create a user friendly application
Operational changes |  |  | It’s the responsibilty of the project manager and team manager to communicate any changes in the project with the team
Lack of experience on handling personal data, |  |  | Proper training has to be provided to the team from the sponsor before intiation of the project. It’s the responsibility of the project manager to check each and every member of the team are well trained
Technical glitches while integrating application with EHRs |  |  | Compatible softwares have to be acquired in order to extract the whole information from EHR's
No control of access to external databases |  |  | It’s the responsibility of the team manager and project manager to provide all the resources to the team
Scope creep |  |  | Its one of the main responsibility of the project manager to check with the team members that they are on the right track and in complaince with the scope of the project
Budget constraints |  |  | Project sponsor has to take the whole responsibility that there are no constraints in the budget allocation to the project
Analysis of mobile application |  |  | There should be a special testing team to analyze the mobile application usage and its feasability in the market. Upgradation can be done by this team to improve the downloads.
Low performance |  |  | The Project manager need to have a check on the performances of the team members and need to communicate with them if there are lacking in any aspect
Lack of data strategy |  |  | Proper stratergy has to be planned by the project manager and had to be communicated with the team members.
Change in legal requirements by regulatory authorities |  |  | Legal requirements by regulatory authorities has to be the complete responsibility of the Project sponsor
Data loss |  |  | Project manager have to be very careful and need to give a heads up that how data plays a crucial role and inform them there should be no data loss
Health data Misuse or data theft |  |  | Project manager along with the Security team has to be careful that there should no health data misuse or data theft